## Sheet1
Url: | https://www.spacefoundation.org/
Title / Role | Foundation Visitor | Development Team | Corporate Members | Site Maintainers | Foundation Board
Stake in Project | High, the project is for the end user's benefit. | Moderate, They will be responsible for the creation and development of the site and potentially any fixes or changes to the site | Moderate, they are part of the foundation and thus benefit from its success. | High, they are responsible for the site during it's lifespan | High, The site represents the foundation that they are in charge of.
Impact in the Project | Moderate to None | High | Minimal | Moderate | High
Deliverables for successful project | Opinions on the use of the site when asked | Design documents, Site code, Wireframes, a way to track issues and their resolution, etc. | Input during the final testing of the new site. | Any demands for the maintaince of the site, to include documentation anf processes | List of requirements of what the site should be achieving. As well as modifications to those requirements throguh the development process.
Perceived Attitudes about the project | a Range from excited to participate to uninterested | Proffesional, they are being paid to design and build the site. Enthusiastic. | Heppy about the improvement and just want the site to relay in the information in a proffessional manner. | Proffesional, this group will be responsible for the upkeep of the site. Might be hesitant to a learning a new site and all of it's qwirks. | Presonal and Proffesional, hopefully excited for the ability to better represent their company.
Management strategy or involvement | Minimal involvement | High envolvement, management of the company they work for. | Minimal involvement but should be kept informed when major milestones are hit | Moderately involved in the design process, highly involved in the testing and issue tracking. Work closely with this group to better understand their needs for running the newly developed site. | Highly involved, should be included in each step of the development process and will direct the project throughout its life.
Stakeholder Responsibilities | Providing feedback when asked, otherwise nothing | Responsible for the design and building of the site to include delivering a working site meeting the requirements of the customer(s) | No responsibilities | Responsible fo maintaining and fixing the site during it's lifespan. | Responsible for reviewing the site and its contents to make sure it aligns with the foundations goals going forward.